## Issues
No | Issues | Status | Priority
1 | Persisit details in the cart.jsp till payment page. | Fixed | High
2 | Complete one entire flow of payment. - Save each cartline to DB by getting the values at runtime. - Hold the orders page till payemt is finished. Should be able to go back to items page even from the payment page. | Inprogress | High
3 | Fix the login issue. First page displayed should be login. |  | High
4 | Updating a user - not working. It adds a new user. getId() is coming as 0. |  | Low
5 | Fix below warning a. Establishing SSL connection without server's identity verification is not recommended. According to MySQL 5.5.45+, 5.6.26+ and 5.7.6+ requirements SSL connection must be established by default if explicit option isn't set. For compliance with existing applications not using SSL the verifyServerCertificate property is set to 'false'. You need either to explicitly disable SSL by setting useSSL=false, or set useSSL=true and provide truststore for server certificate verification. |  | Low
6 | Add items to cart. Increment the count. Decrement is possible after 1. |  | Low
7 | Column size keeps on varying on clicking + and - in cart. |  | Low
8 | Date and time returned in the History page is not formated. |  | High
9 | Join Category and sub-category table and display the category name in Manage Subcategory tab. |  | High
10 | Text not centered in category/sub-category/product buttons - ( btn-item in css) |  | Low
11 | History page - |  | Low
12 | a. Hide the column 'Staff Id' when staff is logged-in |  | Low
13 | b. Show staff NAME, for Admin login ( Join columns and get the staff name ) |  | Low
14 | Pure Bootstrap
15
16
17
18
19
20
21
22
23
24

## Doubt
<%@include file="payment.jsp"%> - Is it right?
After payment, re-route to Home ?
How to get values from JSP page from controller.

## Features
No | Issues | Status | Priority
1 | Settings feature\UI
2 | Reporting Feature\UI
3 | Integrating with AWS
4 | Printing receipt
5 | Receive scanner input + runtime search